## Sheet1
Python E-hub Model Development Plan - Build v2.0
Building upon existing UESL Python e-hub tool (Boran's work, v1.0)
Priority | Item ID | Development item | Status | Solution | Tested? | Date | Notes | Original order
2 | 9 | Restrictive assumption; electricity always assumed as an energy carrier | Solved | Removed this requirement |  | 2018-02-13 | Related to 55 | 1
3 | 18 | Change solar capacity to kW (instead of m2); requires user to specify kW/m2 input for each technology | Solved | Solar capacity now in kW; solar specific power (kW/m2) input introduced |  | 2018-02-13 | Affects input table and several equations (also linked to item 10) | 2
2 | 10 | Input improvement; potential for user error. It is not clear that "Area" input table entry should be used exclusively for solar technologies (e.g., should at least be changed to “solar rooftop area”) | Solved | No longer used; changed to solar specific power |  | 2018-02-13 |  | 3
3 | 11 | Restrictive assumption; Area (m2) == 0 for dispatch technology identification | Solved | No longer used |  | 2018-02-13 |  | 4
3 | 29 | Restrictive assumption; CHP technologies identified as those techs with output >1 (other techs could also have more than one output) | Solved | CHP equations no longer used; this is now a multi-output tech |  | 2018-02-13 |  | 5
2 | 12 | Input improvement; potential for user error. Excel input sheet should specify that CHP efficiency is interpreted as the efficiency for the energy carrier listed first in the energy output matrix (e.g., electricity); the user should also be aware that this first energy carrier defines the interpretation of capacity (e.g., electric CHP capacity) | Solved | Tried to put this in notes; perhaps could make a user guide to fully explain |  | 2018-02-13 |  | 6
3 | 31 | Initialization problem; maxSolarArea initialization may not be appropriate for all problems; should be an input specified by modeler | Partially solved | This is now a custom constraint |  | 2018-02-13 |  | 7
1 | 32 | maxSolarArea definition requires clarification | Partially solved | Maximum rooftop constraint has been modified to sum over all rooftop techs; however, maxSolarArea could be specified by hub in the input file; or this should be handled as a custom constraint (currently handled as a custom constraint) | Tested with single/multi node files; appears to work | 2017-11-08 |  | 8
2 | 7 | Change index; remove energy carrier from model.Capacities, model.Ytechnologies, model.linCapCosts | Solved | Index removed; model.Ytechnologies removed |  | 2018-02-13 |  | 9
1 | 1 | Change storage to be specified by technology and not energy carrier | Solved | Added index for storage technology; changed related equations, functions and parameters (see documentation) | Tested with single/multi node files; appears to work Tried varying storage energy carriers and number of storage technologies | 2017-11-14 | Assumes only one stored energy carrier per technology | 10
2 | 21 | Allow for other time period definitions (i.e., not just hourly) | Outstanding | Important |  |  |  | 11
2 | 6 | Input improvements; excel titles should be changed for storage capital cost (does not need to be a battery), export price (this is not necessarily the same as a feed in tariff; it is simply the price for the export of an energy carrier, should be clear) | Solved | Input sheet redone |  | 2018-02-13 |  | 12
2 | 13 | Index change; change model.opPrices to be by energy carrier and not technology (otherwise, no flexibility to have multiple inputs to processes) | Solved | Index by EC |  | 2018-02-13 | Related to item 17 | 13
2 | 4 | Index change; feed-in-tariff should be specified by technology as well (e.g., residential PV has different feed-in tariffs than commercial/industrial, also by capacity in residential, and by generated energy in residential); having the FiT by energy carrier is not appropriate | Solved | Can handle this through ECs (i.e., different EC output for PV res vs. PV com) |  | 2018-02-13 | Related to item 37 | 14
2 | 2 | Introduce storage operating cost | Solved | Fixed O&M introduced |  | 2018-02-13 |  | 15
1 | 8 | Index change; remove hub index from technology lifetime parameter | Solved | removed hub index from model.lifeTimeTechs and model.lifeTimeStorages. (However, these parameters not explicitly used in the code.) | Y | 2017-11-09 |  | 16
3 | 25 | Remove model.HeatLosses and model.timeHorizon; these are not used in the model | Solved | Removed |  | 2018-02-13 |  | 17
1 | 33 | Network cost not currently used in the model (commented out in code); this should be added again, along with maintenance costs (OMV) - this is not currently an input to the model | Solved |  | Basic testing with multi node file | 2017-12-04 | Network issue; related to item 19, 20, 34 | 18
1 | 34 | Need to add pipeline sizing, capacity in kW | Solved | User can specify network connection capacity per line | Basic testing with multi node file | 2017-12-04 | Network issue; related to item 49 | 19
3 | 26 | Initialization problem; bigM initialization may not be appropriate for all problems | Partially solved | User specified in the Excel input spreadsheet for the time being; up to user to make sure it is appropriately specified |  | 2018-02-13 |  | 20
3 | 35 | model.loads uses use model.hub_i and not model.hub | Solved | Changed instances of model.hub_i to model.hubs to be consistent |  | 2018-02-13 |  | 21
2 | 36 | Input and code naming improvement: change NPV to CRF (in code: model.NetPresentValueTech and model.NetPresentValueStor) | Solved | NPV is now CRF |  | 2018-02-13 |  | 22
2 | 17 | Index change; change model.P to be by energy carrier as well (otherwise, no flexibility to have multiple inputs to processes) | Solved | Replaced with model.Ein |  | 2018-02-13 | Related to item 13 | 23
2 | 37 | Index change; change model.Pexport to be by technology as well (e.g., this matters for feed-in-tariffs) | Solved | Can handle this through Ecs (i.e., different EC export for PV res vs. PV com) |  | 2018-02-13 | Related to item 4 | 24
3 | 14 | Add capacity factors. If time is allowed to be non-hourly, this constraint could be Energy output <= capacity * time * capacity factor | Partially solved | Annual CF implemented; hourly CF option underway | Basic testing | 2018-03-19 | Related to item 21 | 25
2 | 16 | Restrictive assumption; exports only allowed for electricity; remove constraint setting Eexp_nonelectric = 0 (export_rule) | Solved | User-specified as desired |  | 2018-02-13 |  | 26
1 | 39 | Grid is always assumed currently; could make this optional (e.g., needed for micro grid or self-sufficient energy systems) | Solved | Grid is no longer mandatory; handled through the introduction of import energy carriers | Basic testing with multi node file | 2018-02-13 |  | 27
1 | 40 | Error in part load lower bound constraint | Solved | Modified part load lower bound (partLoadL_rule) constraint | Tested with single/multi node files; appears to work | 2017-11-06 |  | 28
1 | 19 | Code does not allow new pipelines to be installed in the model (fixednetwork=1 in line 912) | Solved | Connection capacity can be specified or optimized. If user provides capacity for a connection, this is fixed. If user leaves capacity blank, model cost optimally invests. | Basic testing with multi node file | 2017-12-04 | Network issue; related to item 33, 20, 34 | 29
1 | 30 | Error; storage balance constraint should have (1-standby loss)*SOC | Solved | Modified storage balance (storageBalance) constraint | Test with single node file: works Test with multi node file: negative objective; something is wrong with model… | 2017-11-08 | Before item 41 was implemented, this change resulted in a negative objective function (as the start SOC took on the maximum storage value, effectively giving the model free energy) | 30
3 | 28 | No salvage costs, taxes (e.g., carbon tax), subsidies, construction times (relevant in long-term models) - include carbon tax and subsidies at least | Partially solved | Carbon tax introduced | Basic testing with multi node file | 2018-02-13 |  | 31
1 | 20 | Single and multi-hub investment cost constraints are the same; network costs are not included | Solved | Network costs are now included. Investment costs do not apply to existing capacities | Basic testing with multi node file | 2017-12-04 | Network issue; related to item 19, 33, 34 | 32
3 | 23 | Why is second total carbon variable (TCO2_2 in documentation) needed? | Solved | Has to do with Pyomo requirement (TotalCarbon2 declared in the objective) |  | 2018-02-13 | Probably because of carbon optimization | 33
2 | 24 | model.maxCarbon (max carbon emissions) is declared but never used; there is a commented out max carbon constraint in line 1059; re-implement this; should be a user input and not hardcoded | Solved | Constraint implemented, activated depending on if specified in user input spreadsheet |  | 2018-02-13 |  | 34
2 | 51 | Initialization problem; model.maxCarbon is hardcoded; should be user-specified | Solved | User input in Excel spreadsheet |  | 2018-02-13 |  | 35
1 | 41 | SOC_start = SOC_end; this is commented out in code and needs to be manually uncommented by user; improve implementation | Solved | Introduced 2 new constraints: storageStartEnd_rule, initSoc_rule | Tested with single/multi node files; appears to work | 2017-11-15 | Related to item 42 NOTE: currently SOC_start = storage capacity * minimum SoC; however, this should be more flexible. User should be able to input starting SoC for each hub | 36
1 | 42 | Storage above minimum constraint commented out in code; needed constraint; improve implementation | Solved | Constraint re-implemented: storageMinState_rule | Tested with single/multi node files; appears to work | 2017-11-15 | Related to item 41 | 37
2 | 43 | Change load balance constraint to be an upper bound rather than a fixed constraint; adds flexibility (also done in Evins' code) | Solved | Not currently implemented |  | 2018-02-13 |  | 38
2 | 44 | Evins' model has all variables >=0 constraint; is there a reason our code doesn't have this? | Solved | Variables are declared as non-negative reals; therefore, this is not needed |  | 2018-02-13 |  | 39
1 | 45 | Make code more modular (keep in mind multi-layer users; certain inputs specified in python file, others in Excel (e.g. custom constraints, change storage initialization)); keep maximum solar rooftop constraint and rooftop_techs as a custom constraint | Solved | big change |  | 2018-02-23 | Related to item 53 | 40
3 | 46 | Specify network losses by m length instead of total loss as a fraction | Solved | losses now specified by user in fraction/m. Model calculates total loss as model.netLoss[l]*model.netLength[l] |  | 2017-12-04 | Network issue | 41
3 | 47 | Network flow (Network activity constraint); see notes; could perhaps make it positive (i.e., hub j to i / i to j instead of negative flows); would then remove negative network activity constraint; would need to add constraint to prevent bidirectional flow during a single time period; user must specify balancing nodes; double check approach | Solved | Flow is now positive; bidirectional flow at single time period is prevented with a constraint |  | 2017-12-04 | Network issue | 42
1 | 48 | Julien suggested changing solar constraint (solarInput_rule) to <= instead of == (see Julien Marquant's email, 07.11.17); I would not advise this; I think this may be related to item 43 | Solved | Below code change: def capacityConst_rule(model, i, t, inp, out): if model.cMatrix[inp,out] <= 0: return(model.P[i, t, inp] * (-1)*model.cMatrix[inp,out]<= model.Capacities[i, inp,out]) else: return (model.P[i, t, inp] * model.cMatrix[inp,out]<= model.Capacities[i, inp,out]) model.capacityConst = Constraint(model.hub_i, model.Time, model.DispTechs, model.Out, rule=capacityConst_rule) New constraint: # - for solar technologies solarkWperm2 = 0.2 # NOTE: solar panel kW/m2 assumption; temporary fix. This should be specified in the user input file. def capacityConstSol_rule(model, i, t, inp, out): return (model.P[i, t, inp] * model.cMatrix[inp,out]<= model.Capacities[i, inp,out] * solarkWperm2) model.capacityConstSol = Constraint(model.hub_i, model.Time, model.SolarTechs, model.Out, rule=capacityConstSol_rule) This is no longer needed since solar cap is now in kW |  | 2017-12-05 | Found an error in capacity constraint (energy <= capacity) - this is applied to solar techs, but this equation doesn't make sense for solar (kWh <= m2). Asked Carlos to implement and test fix to see if it resolves the problem - he reported that it works now. Could also be related to item 43 Past: asked Carlos to test his model by changing load balance constraint to <= ; this didn't help | 43
1 | 49 | Code does not take network capacity as an input for the fixed network | Solved | User can specify network connection capacity per line, this is now read by the code | Basic testing with multi node file | 2017-12-04 | Network issue; related to item 34 | 44
2 | 52 | Include fixed capital costs (Evins' model has this) | Solved | Included for storage, techs, and networks |  | 2018-02-13 |  | 45
2 | 53 | Allow user to specify custom constraints in model structure | Solved | Currently handled through mod_custom.py file |  | 2018-02-23 | Related to item 45 | 46
1 | 54 | Allow user to pre-define installed capacity (i.e., operation optimization only) | Solved | User can specify existing installed capacities per technology. If user provides capacity, this is fixed in the model. If user leaves capacity blank, model cost optimally invests. | Basic testing with multi node file | 2017-12-07 |  | 47
2 | 55 | Order of energy carriers is assumed, starting with electricity, which is hard-coded (e.g., in "def cMatrix"). This should be made flexible! Get rid of "Output" binary matrix in input file. "def cMatrix" needs to be redefined. | Solved | Cmatrix has been replaced; this is now flexible |  | 2018-02-13 | Related to item 9 | 48
2 | 56 | Introduce storage maximum capacity constraint | Solved | Included for storage, techs, and networks, as well as minimum |  | 2018-02-13 |  | 49
2 | 57 | Input improvement; change "min_state" in input sheet to "Minimum SoC (share)" or something similar to clarify the meaning of this input | Solved | Input sheet redone |  | 2018-02-13 |  | 50
2 | 58 | Index change; storage parameters (e.g., max charge rate) do not need hub index, can be removed | Solved | Hub index removed from 7 storage parameters | Y | 2017-11-14 | Related to item 60 | 51
1 | 59 | model.Ystorage binary was being set to zero for single hub model (Carlos/Andrew discovered this problem) | Solved | Problem lay in StorageBinary function; string was being compared to an integer; therefore comparison was never true (1). This has been changed to compared an integer with an integer (i.e., "if j+1==self.StorageData.loc["Hubs"][i]¦") | Y | 2017-11-14 |  | 52
2 | 60 | Index change; technology cost parameter does not need hub index, can be removed | Solved | Cost by tech index only |  | 2018-02-13 | Related to item 58 | 53
3 | 61 | Allow for time-varying input costs (e.g., hourly electricity prices) | Solved | Hourly import energy carrier prices can now be specified | Basic testing | 2018-03-19 | May require if statement type selection of constraints/parameters | 54
1 | 62 | Develop demonstration cases, test code | Partially solved | Developed demonstration cases; could always be added to |  | 2018-03-15 | Stress test further | 55
1 | 63 | Fixed O&M not currently being used (applies to technologies, storage, network) | Solved | Implemented for techs, storage, networks | Basic testing with multi node file | 2018-02-13 | Related to item 2, 20 | 56
1 | 64 | Develop export of results (e.g. pivot tables) | Solved | Results now export to a text file. An Excel file has also been setup to read the text file and generate pivot tables for a user to easily see the result variables. | Tested with basic files; should be tested with larger files for real cases | 2017-12-14 |  | 57
1 | 65 | Have flexibility to specify single or bi-directional network connections | Solved | By default, line is bi-directional. User can specify (per line), if the line should be uni-directional instead in the input file |  | 2017-12-05 | Network issue | 58
3 | 66 | User must comment and uncomment objective function in code; this should be a user input through Excel | Solved | User input in Excel spreadsheet |  | 2018-02-13 |  | 59
1 | 67 | Error found: Ytechnologies is always set to 1 | Solved | Corrected with the implementation of the constraint equation model.Ytechnologies[i, inp,out] <= model.Capacities[i, inp,out]; update: Ytechnologies has been removed |  | 2018-02-13 |  | 60
1 | 68 | Improve input sheet/reading; e.g., when network or storage is deleted, code fails | Solved | Network and storage inputs not required |  | 2018-02-13 |  | 61
1 | 69 | Demand data must be provided for all energy carriers in the same order and for each hub; very limited flexibility. Modify to give user flexibility | Solved | Can be specified as the user desires |  | 2018-02-13 | Needed in order to move away from "Out" being defined as the number of demands, and moving towards defining "Out" as any energy carrier (demand or not). This must be fixed so that an error does not arise in accessing the demand for an EC with no direct demand (e.g., a fuel, such as wood). | 62
1 | 70 | Fix carbon optimization; implementation of max carbon; declaration of objective | Solved | Carbon objective minimization and max carbon input in spreadsheet | Basic testing with multi node file | 2018-02-13 |  | 63
2 | 71 | Clean up code (comments, syntax, etc.) | Solved |  |  | 2018-02-23 |  | 64
1 | 72 | Redo input spreadsheet; make sure empty fields are interpreted correctly and can be left blank | Solved | Redone to allow more flexibility | Test further | 2018-02-13 |  | 65
1 | 73 | VOM can take on a negative value if cMatrix efficiency is negative | Solved | Replaced cmatrix; efficiencies no longer negative |  | 2018-02-13 |  | 66
3 | 74 | Label technologies from 1 rather than from 2 (where 1 is the fixed grid) | Solved | Techs not labeled starting from 1 | Y | 2018-02-13 |  | 67
2 | 75 | Max cap required; should be flexible if user wants cap or not | Solved | User can leave this field blank; if blank, max cap < infinity |  | 2018-02-13 |  | 68
1 | 76 | Multi-input/output technologies should be allowed | Solved | User input in Excel spreadsheet. Categories of techs: multi-output fixed shares, multi-input fixed shares, and techs without fixed shares specified; these categories are treated separately | Basic testing with multi node file; test further | 2018-02-13 |  | 69
1 | 77 | Fixed input and output shares should be allowed | Solved | User input in Excel spreadsheet. Categories of techs: multi-output fixed shares, multi-input fixed shares, and techs without fixed shares specified; these categories are treated separately | Basic testing with multi node file; test further | 2018-02-13 |  | 70
1 | 78 | Introduce Ein and Eout variables | Solved | Equations for different tech categories introduced | Basic testing with multi node file | 2018-02-13 |  | 71
1 | 79 | Introduce carbon factors for techs, storage, networks (e.g., LCA or installation) | Solved | Introduced new carbon factors | Basic testing with multi node file | 2018-02-13 |  | 72
1 | 80 | Introduce storage capacity (pre-installed), max cap, min cap | Solved | Introduced | Basic testing with multi node file | 2018-02-13 |  | 73
1 | 81 | Introduce max/min operational output from techs | Solved | Introduced | Basic testing with multi node file | 2018-02-13 |  | 74
1 | 82 | Introduce max import supply constraint | Solved | Introduced | Basic testing with multi node file | 2018-02-13 |  | 75
1 | 83 | Introduce carbon tax for import ECs | Solved | Introduced | Basic testing with multi node file | 2018-02-13 |  | 76
2 | 84 | Potential for efficiency improvements/speeding up model runs. There are many sparse variables (i.e., with many zero values), especially for networks. Potential solution could be to generate less equations by creating equations individually (e.g., in loops which test conditions). In general, need to stress test model more to find and address run time/efficiency limitations. | Outstanding | Important |  |  |  | 77
3 | 85 | Allow specification of import energy carriers by hub (could have different prices and limits per hub) | Outstanding |  |  |  | This can be implemented in practice by specifying different energy carriers per hub | 78
3 | 86 | User experience improvement: would be useful to automatically generate an energy flow diagram schematic based on the input file, to allow a user to visualize the energy system they have specified (useful for error checking and model development by a user) | Outstanding |  |  |  |  | 79
3 | 87 | Solar input can be specified by hub in addition to time to provide more flexibility | Outstanding |  |  |  |  | 80
3 | 88 | User experience improvement: cannot input comma-separated hub values for demands (only one hub number can be specified per column); may be good to change this to allow for comma-separated hub values | Outstanding |  |  |  |  | 81
1 | 89 | Improve excel macro input file to allow for faster imports; improve user experience with this spreadsheet in general | Solved |  |  | 2018-03-19 |  | 82
1 | 90 | Complete documentation, upload to GitHub | Solved |  |  | 2018-03-19 |  | 83
Note on E5: Rev: changed documented in "E-hub optimization problem.docx" v3.0+
Note on I5: Rev: Mashael's tracking flag; can be removed later